## Sheet1
1 | Analysis & Desing
1.1 | Define Design Mechanisms (Data Access, Framework, etc) | 5 days
1.2 | Identify Architecturally Signifficant Use Cases | 1 day
1.3 | Build Prototype | 5 days
2 | Integrated Change Management
2.1 | Development Environement Setup | 2 days
2.2 | Server Environment Setup | 3 days
3 | Implementation
3.1 | Browse Products | 3 days
3.2 | CRUD Shopping Cart | 5 days
3.3 | Check Product Availability | 2 days
3.4 | Login | 1 day
3.5 | Checkout
3.5.1 | Input Billing Address | 2 days
3.5.2 | Input Delivery Adress | 2 days
3.5.3 | Input Billing Data | 1 day
3.5.4 | Confirm Order | 1 day
3.5.5 | Clear Credit Card | 3 days
3.6 | Send Email Confirmation
3.6.1 | Send Email | 2 days
3.6.2 | Design Email Template | 3 days